## Slide 1: KOTAK BANK- SALESFORCE
Prepared by- Neha Richhariya
Date: 15-10-2023

## Slide 2: Situation
Kotak Mahindra Bank wants to make customer interactions more digital and seamless through its Salesforce app. The app already covers basic banking, but customers today expect quicker, more personalized and branch-free services. Bank staff also need smarter tools to handle leads, offer the right products, and give better service without extra effort.

## Slide 3: Problem
Fragmented Interactions: Customers still need branch visits or repeated document submissions for many services.
Delayed Responses: Bankers often miss timely opportunities to cross-sell or serve due to lack of real-time insights.
Long Wait Times: Branch queues and manual appointment scheduling cause frustration.
Complex Onboarding: Multiple forms and repeated KYC slow product adoption.

## Slide 4: Opportunity
Implementing these features in Salesforce can:
Enable end-to-end digital servicing (Video Banking + Document Vault).
Provide AI-driven actionable insights (Smart Relationship Alerts) for bankers to proactively engage customers.
Reduce branch dependency and wait times (Appointment & Queue Manager).
Simplify cross-product onboarding (One-Click Product Application).
Together, these create a seamless, paperless, and personalized banking experience, improving revenue and loyalty.

## Slide 5: Purpose Statement
The purpose of this initiative is to enhance Kotak Bank’s Salesforce app with intelligent, customer-centric features that simplify banking, improve banker productivity, and drive deeper customer engagement while reducing operational costs.

## Slide 6: Project Objectives
Improve Digital Engagement:- provide secure video banking and instant document sharing to reduce branch visits by at least 30%
Increase Banker Productivity: - Enable real time alerts and smart scheduling to improve cross-sell opportunities and customer response time.
Enhance Customer Experience: - Offer goal tracking, instant applications, and queue management to reduce wait times and on boarding effort.
Boost Revenue Opportunities: - Use AI-Insights and one-click product applications to increase product penetration (loans, cards, and investment).
Ensure Compliance & Security: - Maintain data security and meet regulatory standards while digitizing processes.
.

## Slide 7: Success Criteria
Customer Adoption: - 50% of app users use at least one new feature within 6 months.
Reduced Branch Visits: - 30% fewer in-branch service requests within 1 year.
Banker Productivity Gains: - 20% less follow-up time with Smart Alerts & Document Vault.
Cross-Sell Revenue Growth: - 15% rise in cross-product applications in the first year.
Customer Satisfaction: - +10 NPS improvement within 6 months.

## Slide 8: Agile Methods
The project will follow an Agile Scrum methodology: -
Product Backlog: Features broken down into Epics → User Stories → Tasks.
Sprints: 2–3 week sprint cycles with continuous delivery of working increments.
Daily Stand-Ups: Quick updates on progress and blockers.
Sprint Review & Demo: Stakeholder feedback at the end of each sprint to refine features.
Sprint Retrospective: Identify improvements for the next sprint.
Continuous Integration/Testing: Frequent builds and testing to ensure quality and quick fixes.
Approach
1. Start with Discovery & Requirements Workshops with bankers, customers, and compliance teams. 2️. Create MVP (Minimum Viable Product) for one key feature (e.g., Integrated Video Banking). 3️.Gradually roll out other features in phased sprints based on priority.

## Slide 9: Key characteristics of Agile Model in this Project
Iterative Development – Deliver small, usable features in short sprints.
Customer Collaboration – Get regular feedback from bankers and customers.
Flexibility – Adapt to changing requirements or priorities quickly.
Continuous Delivery – Release working updates frequently for early value.
Continuous Improvement – Review each sprint to refine processes and performance.

## Slide 10: Resources
People (Human Resources)
Business Analyst, product owner, Salesforce Developers, UI/UX Designers, QA Testers, Security Expert, Training Team.
2. Time
Estimated Total project duration 6-8 months
Discovery & Design: - 4-6 weeks.
Development & Sprints: - 4-6 months.
Testing & UAT: - 1-2 months.
Go-Live & Training: - 2-3 weeks.

## Slide 11: Resources
Budget: -
Development & Licensing: - Salesforce customization & integrations- Approx. Rs. 1.5-2.5 Cr.
Infrastructure & Security: - Video banking infrastructure, document storage encryption- Approx. Rs. 50-75 Lakhs.
Training & Change Management: - Approx. Rs. 20-30 Lakhs.
Other Resources: -
Hardware – Servers, laptops, banker tablets, mobile test devices.
Software – Salesforce CRM, AI tools, video banking, document management.
Network – Secure high-speed internet, VPN, cloud connectivity.
Data Infrastructure – Data warehouse, encrypted storage, backup & recovery.
Security – Firewalls, multi-factor authentication, end-to-end encryption.

## Slide 12: Risks
Data Privacy & Security – Sensitive customer data in video banking or document vault could face breaches.
Integration Challenges – Linking Salesforce with legacy systems may cause delays or technical issues.
Low User Adoption – Customers or bankers might resist using new features.
Budget Overrun – Development or integration costs may exceed the planned budget.
Regulatory Changes – New RBI or compliance rules could require rework or feature adjustments

## Slide 13: Dependencies
Regulatory Approvals – RBI/KYC norms for video banking and document storage.
Salesforce Platform Readiness – Availability of APIs for video and document integrations.
Third-Party Vendors – Secure video conferencing provider, cloud storage vendor.
IT Infrastructure – High-speed internet and mobile app support for real-time services.
Training & Change Management – Timely training of bankers and support staff.

## Slide 14
THANK YOU